## Slide 1: Olympus HRIS
Project overview, what is left, and the plan to launch in Bangladesh
Board meeting · October 2026
Notes: Purpose of today: show what the product does, how far it is built, what is still missing, and what we need to decide to launch in Bangladesh.

## Slide 2: The product is mostly built; the business is not yet
67%
of planned features are live on the server
73%
are built, counting transport waiting to deploy
20
features left, 7 of them are new modules
Core HR, attendance, payroll with Bangladesh tax / PF / gratuity, hiring, notices, helpdesk, the AI assistant and document management are live.
Transport (vehicles, drivers, trips, fuel, maintenance, costs) is built; deployment and testing come next.
To sell, we still need: a pilot with real companies, billing, legal and tax set-up, support, and a few product gaps closed.
Ask today: approve a 3–5 company pilot and the launch budget (slide 18).
Notes: Percentages count features in the tracker: 50 live, 5 built and waiting to deploy (transport steps 1–5), 20 not started (75 in total).

## Slide 3: The problem we solve for Bangladeshi employers
1
Excel and paper
Attendance, leave and salary sheets are kept by hand; mistakes reach the payslip.
2
Changing law every budget
Income tax slabs, TDS, PF and gratuity rules change; small HR teams cannot keep up.
3
Buyer and ISO audits
Factories must show licences, safety records and policies on demand, often scattered.
4
Expired licences
Trade, fire, boiler and factory licences lapse because nobody tracks the 30 June deadlines.
5
Foreign tools do not fit
Global suites are priced in USD and do not know the Labour Act, Bangla payslips or local holidays.
6
Hiring on WhatsApp
CVs, tests and interviews are not tracked; good candidates are lost.

## Slide 4: One system, eight areas: what each one does today
Core HR
Company structure, employees, roles and field-level access, portal logins, audit trail
Live
Time & attendance
Shifts, roster, web / GPS / QR check-in, leave, overtime, shift swaps
Mostly live
Payroll
Salary structure, increments, payroll runs, Bangla / English payslips, tax, PF, gratuity
Mostly live
Hiring
Workforce plan, job posts, AI CV screening, tests, interviews, offers, joining
Live
Communication
Notices with read receipts, helpdesk with office-hours SLA, password requests
Live
AI assistant
Answers from company policies and the app guide; never reads employee data
Live
Documents (DMS)
Licences with expiry alerts, review and approval, ISO checklist, retention
Live
Transport (TMS)
Vehicles, drivers, trips with GPS points, fuel with fraud flags, maintenance, cost per km
Built, to deploy
Notes: Mostly live = the area is live with a few items left (devices, scheduled jobs; hours compliance and grievances in payroll). Assets, travel & expense, reports and integrations are not started (slide 13).

## Slide 5: Progress by area: 50 of 75 features live
Chart: 
| Core HR | Time & attendance | Payroll | Hiring | Communication | AI assistant | Documents (DMS) | Transport (TMS) | Other new modules
Live | 11 | 9 | 5 | 9 | 3 | 7 | 6 | 0 | 0
Built, to deploy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
Not started | 2 | 3 | 3 | 0 | 0 | 1 | 3 | 1 | 7
How to read it
Live: on the production database and tested.
Built, to deploy: code and tests done; waiting to be applied and tested in the browser.
Not started: designed in the plan, no code yet.
Engineering base: 50 database steps, 34 automated database test suites, 196 unit tests.
Notes: Source: docs/FeatureTracker.md. A feature is one line in the tracker, so the bars count items, not effort.

## Slide 6: Built for Bangladesh, not translated for it
1
Labour law regimes
Weekly off, leave and overtime rules per law; values confirmed by the company before use.
2
Tax, TDS, PF, gratuity
Income tax slabs and TDS ledger, PF interest and withdrawal, gratuity liability.
3
Bangla where it matters
Payslips, notices and the assistant in বাংলা and English.
4
30 June fiscal year
Trade licence and IRC / ERC expiries default to 30 June; renewals are tracked.
5
Local working week
Friday off, company holidays and office hours count in every deadline and SLA.
6
Mobile number login
Staff without email sign in with a Bangladeshi mobile number.
Notes: Mobile login needs the SMS provider switched on in Supabase before launch (slide 13).

## Slide 7: People, time and pay: the daily core
Core HR
Branches, offices, departments, grades
Employee profile, history, reporting lines
Role permissions down to single fields
ID cards, photos, signatures, NID
Every change in an audit trail
Time & leave
Shifts incl. night, roster, swaps
Check-in by web, GPS fence or office QR
Late, half day, overtime worked out daily
Leave balances, approval, rollover
Month lock before payroll
Payroll
Salary templates and components
Increments with arrears, bonuses, loans
Run → review → approve (maker-checker)
Bank / cash payment sheets
Tax, TDS, PF, gratuity ledgers

## Slide 8: Hiring: from a vacancy to a joined employee
1
Plan headcount
2
Approve vacancy
3
Post job
4
Screen CVs with AI
5
Test & interview
6
Offer
7
Join
Workforce planning per department and a vacancy approval flow before any job is posted.
Public careers page with a QR poster; candidates apply without an account.
AI reads CVs with the company's own key and scores them; HR always decides.
Online written tests, interview scheduling, interviewer score sheets, email / SMS messages.
Offer letters, pre-joining forms, document checks, then one click makes the employee record.

## Slide 9: Communication and the AI assistant
Communication
Notices to all, a department, a branch or chosen people, in Bangla and English, with email copy
Read receipts and "I have read and agree" acknowledgements
Helpdesk tickets routed by category, SLA counted in office hours, rating and auto-close
"Forgot password? Ask HR" for staff without email
AI assistant
Answers "how do I…" questions and points to the right page
Answers policy questions from the company's own documents, with sources
Never reads the employee database; each role sees only what Admin allows
Each company uses its own API key (Claude, OpenAI or Gemini) and pays its own usage
Live test with a real key is still pending

## Slide 10: Documents: licences, approvals and ISO evidence
Upload once, named by the system
HR-POL-0012_v3: department, type, number, version. No duplicate files, full version history.
Licence expiry
Days left for every licence; reminders at 60, 30 and 7 days; a renewal task to the person responsible.
Review before publish
Uploads wait for Admin or manager approval; overdue reviews are flagged, never auto-approved.
ISO checklist
ISO 9001, 27001, 14001, 45001 and more: which clause has evidence and which is a gap.
Retention and disposal
Keep-for rules per type, legal hold, two-person disposal with proof.
Feeds the AI
Approved company-wide policies answer staff questions; confidential files never leave.
Notes: Status: all six steps are live and tested on the server. A strong selling point for garment and export factories facing buyer audits.

## Slide 11: Transport: vehicles, drivers, fuel and cost per km
Vehicles and papers
BRTA registration, fitness, tax token, route permit and insurance in the document library, with expiry alerts.
Drivers
Employees or outside drivers; licence class checked against the vehicle; expired licences flagged.
Trips
Staff request a vehicle, the manager approves, the desk assigns; no double booking.
Location
The driver's phone records odometer and GPS at start, end and each fuel fill; never in the background.
Fuel fraud checks
Octane, diesel, CNG (m³): more than the tank holds, odometer going back, wrong price, low km per litre.
Maintenance and cost
Service by km or months, job cards, parts and tyre stock; cost per vehicle and per km.
Notes: Status: all five steps are built and tested; they go live after deployment. Phase 2: GPS tracker devices and a live map.

## Slide 12: Security and reliability: what a client will ask us
1
Each company is sealed off
Every record carries its company; the database itself refuses cross-company access.
2
Least access
Permissions per role and per field; salary and NID hidden unless allowed.
3
Nothing is silently lost
No hard deletes; every change is in an audit trail.
4
Money needs two people
Payroll, increments and disposals need a second person to approve.
5
Secrets stay secret
API keys stored encrypted; only the last 4 characters are ever shown.
6
Tested
34 automated database test suites and 196 unit tests run on every change.
Notes: Before selling to larger clients we still recommend an outside security test (slide 14).

## Slide 13: Product work left, in priority order
When | What | State
Before pilot | Deploy and browser-test Transport (TMS) steps 1–5 | Built; deploy and test
Before pilot | Live test of the AI assistant with a paid API key | Needs a key
Before launch | Account lockout, SMS provider for mobile login | Supabase settings + SMS vendor
Before launch | Scheduled jobs: daily attendance close, leave rollover, reminders | Turn on the scheduler
Before launch | Bulk import of employees from Excel (suggested) | Not started; speeds onboarding
Before launch | Subscription billing and online payment (suggested) | Not started
After launch | Biometric devices, mobile app with live tracking | Not started
After launch | Hours compliance, grievances, committees; employer cost report | Not started
Later | Assets, travel & expense, reports, integrations; GPS devices and live map | Not started
Notes: Excel import and billing are our suggestions: without them every new client needs manual data entry and manual invoicing.

## Slide 14: Business readiness: what we need before we can sell
Legal & tax
Company and trade licence for a software business
TIN, BIN / VAT registration; confirm VAT on SaaS with a tax adviser
Client contract, privacy policy, data processing terms
Law content
Labour-law expert checks leave, overtime and gratuity values
Tax adviser checks slabs and TDS each budget (July)
A yearly update routine for rule changes
Data & security
Decide hosting region and tell clients where data lives
Backups with a tested restore
Outside security test before large clients
Payments & billing
Collect by bank, bKash / Nagad or a payment gateway
VAT-compliant invoices
Payroll bank files for local banks
Support & onboarding
Bangla-speaking support line and ticket hours
Onboarding service: structure, data import, training
Help guide and short videos
Sales & marketing
Pilot case studies from 3–5 companies
Price list in BDT
Partner channel: HR consultants, accountants
Notes: These are recommendations to confirm with a lawyer and a tax adviser; none of them is done yet.

## Slide 15: Suggested go-to-market for Bangladesh
Who to sell to first
Garment and export factories (200–3,000 staff): payroll, attendance, licences, buyer audits
Mid-size companies (50–500 staff) in Dhaka and Chattogram moving off Excel
IT and service firms that want hiring, documents and ISO 27001 evidence
Companies with vehicle fleets: papers, fuel control and cost per km
How to price and sell
Price per active employee per month, in BDT, with a minimum per company
Plans already in the product: Trial, Basic, Pro, Enterprise
Free trial, then a discount for yearly payment
Paid onboarding package for data import and training
Set the final prices after the pilot, from what pilot companies will pay
Notes: Staff ranges are suggestions for targeting, not market data.

## Slide 16: Roadmap to a paid launch
Nov 2026
Finish and test
Deploy transport steps 1–5
Full test round, fix issues
AI test with a paid key
Lockout, SMS, scheduler
Dec 2026 – Jan 2027
Pilot
3–5 companies, at least one factory
Excel import, billing
Legal, tax and support set-up
Feb – Mar 2027
Paid launch
Prices from the pilot
Case studies, partners
Support hours and help guide
Apr – Jun 2027
Grow
Biometric devices, mobile app
Reports, compliance, grievances
Budget-season tax update (July)
Suggested pilot exit criteria: each pilot company runs at least one real payroll and one month of attendance; no critical bug open for two weeks; each gives written feedback on the price.
Notes: Dates are a proposal; the pilot start depends on finishing the November test round.

## Slide 17: Main risks and how we handle them
Wrong legal or tax values in payroll
Expert review before launch; the company confirms values before they apply; yearly update routine
Data protection rules tighten
Clear hosting disclosure, data processing terms, audit trail and access controls already in place
Slow adoption: HR teams used to Excel
Excel import, onboarding service, Bangla support, a factory pilot as proof
AI cost or wrong answers
Company uses its own key with a monthly cap; answers cite sources; AI never sees employee data
Small team, many modules
Launch with what is live; add modules by paying-client demand

## Slide 18: Decisions we ask from the board
1
Approve a 3–5 company pilot from December 2026, with at least one factory
2
Approve the launch budget: hosting, AI and SMS usage, legal and tax advice, security test
3
Agree the pricing model (per employee per month, BDT) to test in the pilot
4
Name owners for sales, support and legal set-up
Notes: Close: the product core is ready for a pilot; the remaining risk is on the business side, which these decisions address.